## SHOP DRAWING MEP
PROJECT | : THE VIEW II | [17 empty] | 61.17% | A | : Approval
SUBJECT | : MEP SHOP DRAWING MONITORING | [17 empty] | 27.67% | B | : Approved with comment
MAIN-CON | : SOMA CONSTRUTION & DEVELOPMENT CO., LTD | [17 empty] | 15.05% | C | : Return/Reject
CLIENT | : HOHSIN DEVELOPMENT CO., LTD | [17 empty] | 0% | U/R | : Under Review
LOCATION | : #13, ST. 588 CORNER ST.307, PHUM 11, BOEUNG KAK 2, KHAN TOUL KOK, PHNOM PENH | [17 empty] | 206 | Infor. | : For information
PROGRESS | :02/28/2025
No. | Shop DRAWING DESCRIPTION | LASTEST APPROVAL STATUS | SUBMISSION DATE | DT.No. | Rev.A |  |  | Rev.B |  |  | Rev.C |  |  | Rev.D |  |  | Rev.E |  |  | COMMENT | REMARK | Rev.F |  |  | Rev.G |  |  | Rev.H
[5 empty] | SUBMITTED DATE | RETURNED DATE | STATUS | SUBMITTED DATE | RETURNED DATE | STATUS | SUBMITTED DATE | RETURNED DATE | STATUS | SUBMITTED DATE | RETURNED DATE | STATUS | SUBMITTED DATE | RETURNED DATE | STATUS |  |  | SUBMITTED DATE | RETURNED DATE | STATUS | SUBMITTED DATE | RETURNED DATE | STATUS | SUBMITTED DATE | RETURNED DATE | STATUS
MEP SYSTEM
A | Under Basement Floor
II | Plumbing
1 | Shop drawing Plumbing for Pipe Sleeve and Combine drawing layout under BF | A | 2023-09-01 | DT-MEP-042 | 2023-08-17 | 2023-08-18 | C | 2023-08-24 | 2023-08-25 | C | 2023-08-31 | 2023-09-01 | A
2 | Shop drawing of Plumbing for Stormwater Drainage system layout Under BF | A | 2023-09-28 | DT-MEP-078 | 2023-09-19 | 2023-09-20 | B | 2023-09-27 | 2023-09-28 | C | 2023-06-12 | 2023-06-29 | C | 2023-07-12 | 2023-07-13 | C | 2023-07-25 | 2023-07-26 | C |  |  | 2023-08-08 | 2023-08-09 | C | 2023-08-11 | 2023-08-12 | B | 2024-08-21 | 2024-08-22 | A
3 | Shop drawing of Plumbing Cold water supply system layout at Under BF | A | 2023-08-18 | DT-MEP-043 | 2023-08-05 | 2023-08-09 | C | 2023-08-17 | 2023-08-18 | A | 2023-06-12 | 2023-06-29 | C | 2023-07-12 | 2023-07-13 | C | 2023-07-25 | 2023-07-26 | C |  |  | 2023-08-08 | 2023-08-09 | C | 2023-08-17 | 2023-08-18 | A
4 | Shop drawing of Pipe Sleeve layout under BF | A | 2023-08-12 | DT-MEP-037 | 2023-08-05 | 2023-08-09 | B | 2023-08-11 | 2023-08-12 | A
B | Basement Floor
I | Electrical
5 | Shop drawing of Combine Embedded uPVC Conduit system at BF | C | 2023-10-03 | DT-MEP-094 | 2023-09-28 | 2023-10-03 | C
6 | Shop drawing of Cable Tray system at BF | C | 2023-10-03 | DT-MEP-096 | 2023-09-28 | 2023-10-03 | C
7 | Shop drawing of Lighting system at BF | C | 2023-09-18 | DT-MEP-067 | 2023-09-12 | 2023-09-18 | C
8 | Shop drawing of Socket system at BF | C | 2023-09-18 | DT-MEP-057 | 2023-09-01 | 2023-09-05 | C | 2023-09-12 | 2023-09-18 | C
9 | Shop drawing of Electrical for MVAC system at BF | C | 2023-09-18 | DT-MEP-071 | 2023-09-13 | 2023-09-18 | C
10 | Shop drawing of Fire Alarm system at BF | C | 2023-09-18 | DT-MEP-069 | 2023-09-12 | 2023-09-18 | C
11 | Shop drawing of CCTV system layout BF | C | 2023-09-18 | DT-MEP-068 | 2023-09-12 | 2023-09-18 | C
12 | Shop drawing of Public Address system at BF | C | 2023-09-18 | DT-MEP-070 | 2023-09-13 | 2023-09-18 | C
13 | Shop drawing of Access Control system at BF | C | 2023-10-03 | DT-MEP-095 | 2023-09-28 | 2023-10-03 | C
II | Plumbing
14 | Shop drawing of Pipe Sleeve layout under BF | A | 2023-08-12 | DT-MEP-037 | 2023-08-05 | 2023-08-09 | B | 2023-08-11 | 2023-08-12 | A
15 | Shop drawing Plumbing for Pipe Sleeve and Combine drawing layout BF | B | 2023-10-06 | DT-MEP-080 | 2023-09-19 | 2023-09-20 | C | 2023-09-27 | 2023-10-06 | B
16 | Shop drawing of Combined sleeve and opening on GF slab BF | B | 2023-10-10 | DT-MEP-105 | 2023-10-07 | 2023-10-10 | B
17 | Shop drawing of Combined service MEP-system at BF | C | 2023-10-10 | DT-MEP-104 | 2023-10-07 | 2023-10-10 | C
18 | Shop drawing of Fire Fighting system and Combine service drawing layout BF | A | 2023-08-30 | DT-MEP-044 | 2023-08-17 | 2023-08-18 | C | 2023-08-24 | 2023-08-30 | C | 2024-09-05 | 2024-09-19 | A
19 | Shop drawing of Plumbing for Storm Water system layout BF | A | 2023-08-22 | DT-MEP-039 | 2023-08-11 | 2023-08-12 | B | 2023-08-21 | 2023-08-22 | A | 2024-09-05 | 2024-09-17 | B | 2024-10-08 | 2024-10-17 | A
20 | Shop drawing of Plumbing for Waste water Drainage system layout BF | A | 2023-09-20 | DT-MEP-077 | 2023-09-19 | 2023-09-20 | C | 2023-09-27 |  | B | 2024-09-06 | 2024-09-19 | A
21 | Shop drawing of Plumbing Cold water supply system layout at BF | A | 2023-09-28 | DT-MEP-076 | 2023-09-19 | 2023-09-20 | B | 2023-09-27 | 2023-09-28 | B | 2024-09-05 | 2024-09-17 | B | 2024-10-08 | 2024-10-17 | A
22 | Shop drawing of Pipe Sleeve on slab at BF | B | 2023-09-18 | DT-MEP-064 | 2023-09-11 | 2023-09-18 | B
23 | Shop drawing of Plumbing for Fire Fighting system layout BF | A | 2023-09-28 | DT-MEP-079 | 2023-09-19 | 2023-09-20 | C | 2023-09-27 | 2023-09-28 | B | 2024-09-05 | 2024-09-17 | A
24 | Shop drawing of Plumbing at under BF | C | 2023-08-10 | DT-MEP-032 | 2023-06-12 | 2023-06-29 | C | 2023-07-12 | 2023-09-28 | C | 2023-07-26 | 2023-07-26 | C | 2023-08-09 | 2023-08-10 | C
25 | Shop drawing of Fire Fighting system layout under BF | B | 2023-09-01 | DT-MEP-048 | 2023-08-24 | 2023-08-30 | C | 2023-08-31 | 2023-09-01 | B
III | MVAC
26 | Shop drawing of MVAC system at BF | C | 2023-10-03 | DT-MEP-097 | 2023-09-28 | 2023-10-03 | C
C | Ground Floor
I | Electrical
27 | Shop drawing of the Lighting system at GF | B | 2023-11-13 | MEP-102 | 2023-10-07 | 2023-10-26 | C | 2023-11-04 | 2023-11-13 | B
28 | Shop drawing of Socket system at GF | C | 2023-11-13 | MEP-103 | 2023-10-07 | 2023-10-26 | C | 2023-11-04 | 2023-11-13 | C
29 | Shop drawing of Electrical for MVAC system at GF | C | 2023-11-13 | MEP-125 | 2023-11-04 | 2023-11-13 | C
30 | Shop drawing of DB-single line diagram at GF | C | 2023-11-13 | MEP-126 | 2023-11-04 | 2023-11-13 | C
31 | Shop drawing of CCTV system at GF | C | 2023-11-13 | MEP-127 | 2023-11-04 | 2023-11-13 | C
32 | Shop drawing of Fire Alarm system at GF | C | 2023-11-13 | MEP-128 | 2023-11-04 | 2023-11-13 | C
33 | Shop drawing of Public Address system at GF | B | 2023-11-13 | MEP-129 | 2023-11-04 | 2023-11-13 | B
34 | Shop drawing of Acces Control system at GF | B | 2023-11-13 | MEP-130 | 2023-11-04 | 2023-11-13 | B
II | Plumbing
35 | Shop drawing of Combine service drawing and Pipe Sleeve at GF | B | 2024-09-06 | MEP-118 | 2023-11-04 | 2023-11-08 | B | 2024-09-06 | 2024-10-17 | B
36 | Shop drawing of Cold Water supply system at GF | A | 2024-09-06 | MEP-119 | 2023-11-04 | 2023-11-08 | B | 2024-09-06 | 2024-10-17 | A
37 | Shop drawing of StormWater Drainage system at GF | A | 2024-09-06 | MEP-121 | 2023-11-04 | 2023-11-08 | C | 2024-09-06 | 2024-10-17 | A
38 | Shop drawng of Waste Water Drainage system at GF | A | 2024-09-06 | MEP-120 | 2023-11-04 | 2023-11-08 | C | 2024-09-06 | 2024-10-17 | A
III | MVAC
39 | Shop Drawing of Air Conditioning system layout GF | B | 2024-10-11 | MEP-423 | 2024-10-11 | 2024-10-17 | B | 2024-11-12 | 2024-11-21 | B
40 | Shop Drawing of Condensate pipe system layout GF | A | 2024-10-11 | MEP-424 | 2024-10-11 | 2024-10-17 | A
41 | Shop drawing of Ventilation system layout GF RevA | B | 2024-10-16 | MEP-429 | 2024-10-16 | 2024-10-17 | B | 2024-11-12 | 2024-11-21 | B
42 | Shop drawing of Fire Fighting system at GF | A | 2023-12-07 | MEP-385 | 2024-09-06 | 2024-10-19 | C | 2024-11-12 | 2024-11-21 | A
D | 2nd Floor
I | Electrical
43 | Shop drawing of Internal Lighting system at 2F | C | 2023-11-23 | MEP-143 | 2023-11-22 | 2023-11-23 | C
44 | Shop drawing of External Lighting system at 2F | C | 2023-11-13 | MEP-123 | 2023-11-04 | 2023-11-13 | C
45 | Shop drawing of Socket system at 2F | B | 2023-11-23 | MEP-145 | 2023-11-22 | 2023-11-23 | B
46 | Shop drawing of CCTV system at 2F | A | 2023-11-23 | MEP-146 | 2023-11-22 | 2023-11-23 | A
47 | Shop drawing of Fire Alarm system at 2F | B | 2023-11-23 | MEP-147 | 2023-11-22 | 2023-11-23 | B
48 | Shop drawing of Public Address system at 2F | B | 2023-11-23 | MEP-148 | 2023-11-22 | 2023-11-23 | B
49 | Shop drawing of Acces Control system at 2F | C | 2023-11-23 | MEP-149 | 2023-11-22 | 2023-11-23 | C
II | Plumbing
50 | Shop drawing of Cold Water Supply system at 2F | A | 2023-12-07 | MEP-167 | 2023-12-01 | 2023-12-07 | C | 2024-09-27 | 2024-10-17 | A
51 | Shop drawing of Waste Water Drainage system at 2F | A | 2023-12-07 | MEP-168 | 2023-12-01 | 2023-12-07 | C | 2024-09-27 | 2024-10-17 | A
52 | Shop drawing of Fire Fighting system at 2F | A | 2023-12-07 | MEP-169 | 2023-12-01 | 2023-12-07 | C | 2024-09-27 | 2024-10-17 | A
III | MVAC
53 | Shop Drawing of Air Conditioning system layout 2F | A | 2024-10-11 | MEP-425 | 2024-10-11 | 2024-10-17 | A
54 | Shop Drawing of Condensate pipe system layout 2F | A | 2024-10-11 | MEP-426 | 2024-10-11 | 2024-10-17 | A
55 | Shop drawing of Ventilation system layout 2F RevA | A | 2024-10-16 | MEP-430 | 2024-10-16 | 2024-10-17 | A
E | 3rd Floor
I | Electrical
56 | Shop drawing of External system at 3F | B | 2023-11-23 | MEP-144 | 2023-11-22 | 2023-11-23 | B
57 | Shop drawing of Internal Lighting system at 3F | B | 2023-12-06 | MEP-159 | 2023-12-01 | 2023-12-06 | B
58 | Shop drawing of Socket system at 3F | B | 2023-12-06 | MEP-161 | 2023-12-01 | 2023-12-06 | B
59 | Shop drawing of CCTV system at 3F | B | 2023-12-06 | MEP-162 | 2023-12-01 | 2023-12-06 | B
60 | Shop drawing of Fire Alarm system at 3F | B | 2023-12-06 | MEP-163 | 2023-12-01 | 2023-12-06 | B
61 | Shop drawing of Public Address system at 3F | B | 2023-12-06 | MEP-164 | 2023-12-01 | 2023-12-06 | B
62 | Shop drawing of Acces Control system at 3F | B | 2023-12-06 | MEP-165 | 2023-12-01 | 2023-12-06 | B
63 | Shop drawing of Combined embedded Upvc Conduit at floor | B | 2023-12-06 | MEP-166 | 2023-12-01 | 2023-12-06 | B
II | Plumbing
64 | Shop drawing of Pipe Sleeve on slab | A | 2023-11-23 | MEP-142 | 2023-11-22 | 2023-11-23 | B | 2023-12-01 | 2023-12-07 | A
65 | Shop drawing of Cold water supply system layout 3F | A | 2023-12-07 | MEP-171 | 2023-12-01 | 2023-12-07 | B | 2024-10-26 | 2024-11-04 | A
66 | Shop drawing of Waste water Drainage system layout 3F | A | 2023-12-07 | MEP-172 | 2023-12-01 | 2023-12-07 | C | 2024-10-26 | 2024-11-04 | A
67 | Shop drawing of Stormwater Drainage system layout 3F | A | 2023-12-07 | MEP-173 | 2023-12-01 | 2023-12-07 | B | 2024-10-26 | 2024-11-04 | A
68 | Shop drawing of Pipe Sleeve in wall 3F and Pipe Sleeve on slab 5F | A | 2023-12-07 | MEP-175 | 2023-12-01 | 2023-12-07 | A
69 | Shop drawing of Fire Fighting system at 3F | A | 2023-12-07 | MEP-174 | 2023-12-01 | 2023-12-07 | B | 2024-10-26 | 2024-11-04 | A
III | MVAC
70 | Shop drawing of AC Condensate system layout 3F | A | 2024-12-12 | MEP-488 | 2024-12-12 | 2024-12-19 | A
F | 5th Floor
I | Electrical
71 | Shop drawing of Combined Embedded uPVC Conduit | B | 2023-12-20 | MEP-189 | 2023-12-13 | 2023-12-20 | B
72 | Shop drawing of Internal Lighting system | B | 2023-12-20 | MEP-185 | 2023-12-13 | 2023-12-20 | B
73 | Shop drawing of Socket system | B | 2023-12-20 | MEP-183 | 2023-12-13 | 2023-12-20 | B
74 | Shop drawing of CCTV system | B | 2023-12-20 | MEP-187 | 2023-12-13 | 2023-12-20 | B
75 | Shop drawing of Fire Alarm system | A | 2023-12-20 | MEP-186 | 2023-12-13 | 2023-12-20 | A
76 | Shop drawing of Public Address system | B | 2023-12-20 | MEP-184 | 2023-12-13 | 2023-12-20 | B
77 | Shop drawing of Access Control system | B | 2023-12-20 | MEP-188 | 2023-12-13 | 2023-12-20 | B
II | Plumbing
78 | Shop drawing of Stormwater Drainage system layout | A | 2024-01-10 | MEP-208 | 2024-01-04 | 2024-01-10 | A
79 | Shop drawing of Fire Fighting system layout | A | 2024-01-10 | MEP-209 | 2024-01-04 | 2024-01-10 | B | 2024-10-31 | 2024-11-21 | A
80 | Shop drawing of Cold water system layout | A | 2024-01-10 | MEP-206 | 2024-01-04 | 2024-01-10 | A
81 | Shop drawing of Waste water system layout | A | 2024-01-10 | MEP-207 | 2024-01-04 | 2024-01-10 | C | 2024-10-31 | 2024-11-21 | A
III | MVAC
82 | Shop Drawing of Ventilation system layout 5F | A | 2024-10-11 | MEP-427 | 2024-10-11 | 2024-10-17 | A
83 | Shop Drawing of Condensate pipe system layout 5F | A | 2024-10-11 | MEP-428 | 2024-10-11 | 2024-10-17 | B | 2024-11-12 | 2024-11-21 | A
G | 6th Floor
I | Electrical
84 | Shop drawing of Combined Embedded uPVC Conduit | B | 2024-01-10 | MEP-221 | 2024-01-06 | 2024-01-10 | B
85 | Shop drawing of Internal Lighting system | B | 2024-01-10 | MEP-215 | 2024-01-06 | 2024-01-10 | B
86 | Shop drawing of Socket system | B | 2024-01-10 | MEP-216 | 2024-01-06 | 2024-01-10 | B
87 | Shop drawing of CCTV system | A | 2024-01-10 | MEP-219 | 2024-01-06 | 2024-01-10 | A
88 | Shop drawing of Fire Alarm system | A | 2024-01-10 | MEP-220 | 2024-01-06 | 2024-01-10 | A
89 | Shop drawing of Public Address system | A | 2024-01-10 | MEP-218 | 2024-01-06 | 2024-01-10 | A
90 | Shop drawing of Access Control system | B | 2024-01-10 | MEP-217 | 2024-01-06 | 2024-01-10 | B
II | Plumbing
91 | Shop drawing of Pipe Sleeve on slab layout | A | 2024-01-10 | MEP-210 | 2024-01-04 | 2024-01-10 | A
92 | Shop drawing of Fire Fighting system layout | B | 2024-01-18 | MEP-225 | 2024-01-16 | 2024-01-18 | B
93 | Shop drawing of Cold & Hot water supply system | A | 2024-01-18 | MEP-226 | 2024-01-16 | 2024-01-18 | B | 2024-11-22 | 2024-11-28 | A
III | MVAC
94 | Shop drawing of Air conditioning system layout 6F & 6MF | A |  | MEP-460 | 2024-11-19 | 2024-12-05 | A
95 | Shop drawing of AC Condensate system layout 6F & 6MF | A |  | MEP-462 | 2024-11-19 | 2024-12-05 | A
96 | Shop drawing of Ventilation system layout 6F & 6MF | C |  | MEP-477 | 2024-12-07 | 2024-12-19 | C
H | 6thMF Floor
I | Electrical
97 | Combined embedded upvc conduit in slab 6MF for LV & ELV system layout | B | 2024-08-21 | MEP-359 | 2024-08-21 | 2024-09-02 | B
98 | Shop drawing of Lighting system | A | 2024-08-13 | MEP-351 | 2024-08-13 | 2024-08-22 | A
99 | Shop drawing of Socket system | B | 2024-08-21 | MEP-360 | 2024-08-21 | 2024-09-02 | B
100 | Shop drawing of electrical for MVAC system | A | 2024-08-21 | MEP-361 | 2024-08-21 | 2024-09-02 | A
101 | Shop drawing of CCTV system | A | 2024-08-13 | MEP-352 | 2024-08-13 | 2024-08-22 | A
102 | Shop drawing of Fire Alarm system | A | 2024-08-13 | MEP-353 | 2024-08-13 | 2024-08-22 | A
103 | Shop drawing of Public Address system | A | 2024-08-13 | MEP-354 | 2024-08-13 | 2024-08-22 | A
II | Plumbing
104 | Shop drawing of Water water Drainage system 6MF | A | 2024-01-18 | MEP-227 | 2024-01-16 | 2024-01-18 | C | 2024-11-22 | 2024-11-28 | A
105 | Shop drawing of Pipe Sleeve on slab layout 6MF | A | 2024-01-18 | MEP-228 | 2024-01-16 | 2024-01-18 | C | 2024-11-22 | 2024-11-28 | A
106 | Shop drawing of Cold & Hot water supply system 6MF | A | 2024-01-18 | MEP-229 | 2024-01-16 | 2024-01-18 | B | 2024-11-22 | 2024-11-28 | A
107 | Shop drawing of Fire Fighting system layout 6MF | A | 2024-01-18 | MEP-229 | 2024-01-16 | 2024-01-18 | A
I | 7th Floor
I | Electrical
108 | Combined Embedded uPVC Conduit in slab | B | 2024-08-28 | MEP-363 | 2024-08-28 | 2024-09-02 | B
109 | Shop drawing of Internal lighting system | C | 2024-08-28 | MEP-364 | 2024-08-28 | 2024-09-05 | C
110 | Shop drawing of Socket system | A | 2024-08-28 | MEP-365 | 2024-08-28 | 2024-09-05 | A
111 | Shop drawing of CCTV system | A | 2024-08-28 | MEP-366 | 2024-08-28 | 2024-09-05 | A
112 | Shop drawing of Fire Alarm system | A | 2024-08-28 | MEP-367 | 2024-08-28 | 2024-09-05 | A
113 | Shop drawing of Public Address system | A | 2024-08-28 | MEP-368 | 2024-08-28 | 2024-09-05 | A
114 | Shop drawing of Access Control system | A | 2024-08-28 | MEP-369 | 2024-08-28 | 2024-09-05 | A
II | Plumbing
115 | Shop drawing of Cold & Hot water supply system layout | B | 2024-01-18 | MEP-231 | 2024-01-16 | 2024-01-18 | B
116 | Shop drawing of Pipe Sleeve on slab layout | A | 2024-01-18 | MEP-232 | 2024-01-16 | 2024-01-18 | A
117 | Shop drawing of Fire Fighting system layout | A | 2024-01-18 | MEP-233 | 2024-01-16 | 2024-01-18 | A
III | MVAC
118 | Shop drawing of Air conditioning system layout 7F&7MF | A | 2024-11-19 | MEP-461 | 2024-11-19 | 2024-12-05 | A
119 | Shop drawing of AC Condensate system layout 7F&7MF | A | 2024-11-19 | MEP-463 | 2024-11-19 | 2024-12-05 | A
120 | Shop drawing of Ventilation system layout 7F&7MF | C | 2024-12-07 | MEP-478 | 2024-12-07 | 2024-12-19 | C
J | 7th MF Floor
I | Electrical
121 | Combined embedded upvc conduit in slab 8F for LV & ELV system | B | 2024-09-10 | MEP-387 | 2024-09-10 | 2024-09-19 | B
122 | Shop drawing of Lighting system | B | 2024-09-10 | MEP-388 | 2024-09-10 | 2024-09-19 | B
123 | Shop drawing of Socket system | B | 2024-09-10 | MEP-389 | 2024-09-10 | 2024-09-19 | B
124 | Shop drawing of electrical for MVAC system | B | 2024-09-10 | MEP-390 | 2024-09-10 | 2024-09-19 | B
125 | Shop drawing of CCTV system | A | 2024-09-10 | MEP-391 | 2024-09-10 | 2024-09-19 | A
126 | Shop drawing of Fire Alarm system | A | 2024-09-10 | MEP-392 | 2024-09-10 | 2024-09-19 | A
127 | Shop drawing of Public Address system | A | 2024-09-10 | MEP-393 | 2024-09-10 | 2024-09-19 | A
II | Plumbing
128 | Shop drawing of Pipe Sleeve on slab layout | C | 2024-01-16 | MEP-234 | 2024-01-16 | 2024-01-18 | C
129 | Shop drawing of Fire Fighting system | B | 2024-01-16 | MEP-235 | 2024-01-16 | 2024-01-18 | B
130 | Shop drawing of Cold & Hot water supply system | B | 2024-01-16 | MEP-236 | 2024-01-16 | 2024-01-18 | B
K | 8th Floor
I | Electrical
131 | Shop Drawing of Combined Embedded uPVC conduit in slab 9F for LV & ELV system | A | 2024-09-27 | MEP-405 | 2024-09-27 | 2024-10-17 | A
132 | Shop drawing of Internal lighting system | A | 2024-10-31 | MEP-442 | 2024-10-31 | 2024-11-04 | C | 2024-12-03 | 2024-12-05 | A
133 | Shop drawing of External lighting system | B | 2024-10-31 | MEP-441 | 2024-10-31 | 2024-11-18 | B
134 | Shop drawing of Socket system | A | 2024-10-31 | MEP-443 | 2024-10-31 | 2024-11-18 | A
135 | Shop Drawing of electrical for MVAC system | A | 2024-09-27 | MEP-406 | 2024-09-27 | 2024-10-17 | A
136 | Shop Drawing of CCTV system | A | 2024-09-27 | MEP-407 | 2024-09-27 | 2024-10-17 | A
137 | Shop Drawing of Fire Alarm system | A | 2024-09-27 | MEP-408 | 2024-09-27 | 2024-10-17 | A
138 | Shop Drawing of Public Address system | A | 2024-09-27 | MEP-409 | 2024-09-27 | 2024-10-17 | A
139 | Shop Drawing of Access Control system | A | 2024-09-27 | MEP-410 | 2024-09-27 | 2024-10-17 | A
II | Plumbing
140 | Shop Drawing of Waste Water Drainage system | B | 2024-08-22 | MEP-286 | 2024-04-23 | 2024-04-25 | C | 2024-08-13 | 2024-08-22 | B
III | MVAC
141 | Shop Drawing of Air Conditioning system layout 8F | B | 2024-12-07 | MEP-479 | 2024-12-07 | 2024-12-19 | B
142 | Shop Drawing of Ventilation system layout 8F | C | 2024-12-07 | MEP-480 | 2024-12-07 | 2024-12-19 | C
142 | Shop Drawing of Air Condensate system layout 8F | B | 2024-12-07 | MEP-481 | 2024-12-07 | 2024-12-19 | B
L | 9-35th Floor
I | Electrical
143 | Shop Drawing of Combined Embedded uPVC conduit for LV & ELV system | A | 2024-09-27 | MEP-411 | 2024-09-27 | 2024-10-17 | A
144 | Shop drawing of Internal lighting system at 9F-12F | A | 2024-10-31 | MEP-445 | 2024-10-31 | 2024-11-18 | B | 2024-12-03 | 2024-12-05 | A
145 | Shop drawing of Internal lighting system at 15F-35F | A | 2024-10-31 | MEP-447 | 2024-10-31 | 2024-11-18 | B | 2024-12-03 | 2024-12-05 | A
146 | Shop drawing of External lighting system at 15F,20F, 26F&31F | A | 2024-10-31 | MEP-444 | 2024-10-31 | 2024-11-18 | A
147 | Shop drawing of Socket system at 9F-12F | A | 2024-10-31 | MEP-446 | 2024-10-31 | 2024-11-18 | A
148 | Shop drawing of Socket system at 15F-35F | A | 2024-10-31 | MEP-447 | 2024-10-31 | 2024-11-18 | A
149 | Shop Drawing of electrical for MVAC system | A | 2024-09-27 | MEP-412 | 2024-09-27 | 2024-10-17 | A
150 | Shop Drawing of CCTV system | A | 2024-09-27 | MEP-414 | 2024-09-27 | 2024-10-17 | A
151 | Shop Drawing of Fire Alarm system | A | 2024-09-27 | MEP-415 | 2024-09-27 | 2024-10-17 | A
152 | Shop Drawing of Public Address system | A | 2024-09-27 | MEP-416 | 2024-09-27 | 2024-10-17 | A
153 | Shop Drawing of Access Control system | A | 2024-09-27 | MEP-417 | 2024-09-27 | 2024-10-17 | A
II | Plumbing
154 | Shop Drawing of Waste Water Drainage system layout 9F-33F | A | 2024-08-13 | MEP-285 | 2024-04-23 | 2024-04-25 | C | 2024-08-13 | 2024-08-22 | A
155 | Shop Drawing of Cold & Hot water supply system layout 8F-35F | B | 2024-04-23 | MEP-284 | 2024-04-23 | 2024-04-25 | B
156 | Shop Drawing of Fire Fighting system layout 8F-35F | B | 2024-04-23 | MEP-283 | 2024-04-23 | 2024-04-25 | B
157 | Shop Drawing of Pipe Sleeve layout on slab layout 9F-35F | A | 2024-04-23 | MEP-282 | 2024-04-23 | 2024-04-25 | A
158 | Shop drawing of Waste water drainage system 36F install under 36F layout 35F | A | 2024-12-07 | MEP-486 | 2024-12-07 | 2024-12-19 | A
III | MVAC
159 | Shop Drawing of Air Conditioning system layout 9F-35F | B | 2024-12-07 | MEP-483 | 2024-12-07 | 2024-12-19 | B
160 | Shop Drawing of Ventilation system layout 9F-35F | C | 2024-12-07 | MEP-484 | 2024-12-07 | 2024-12-19 | C
161 | Shop Drawing of AC Condensate system layout 9F-35F | B | 2024-12-07 | MEP-485 | 2024-12-07 | 2024-12-19 | B
M | 36th Floor
I | Electrical
162 | Shop Drawing of Combined Embedded uPVC conduit for LV & ELV system at 36F | A |  | MEP-504 | 2024-12-23 | 2024-12-26 | A
163 | Shop Drawing of Lighting system layout 36F | C |  | MEP-510 | 2024-12-24 | 2025-01-10 | C
164 | Shop Drawing of Socket Outlet layout 36F | B |  | MEP-511 | 2024-12-24 | 2025-01-10 | B
165 | Shop Drawing of Electrical for MVAC system at 36F | A |  | MEP-492 | 2024-12-19 | 2024-12-26 | A
166 | Shop Drawing of CCTV system at 36F | A |  | MEP-493 | 2024-12-19 | 2024-12-26 | A
167 | Shop Drawing of Fire Alarm system at 36F | A |  | MEP-494 | 2024-12-19 | 2024-12-26 | A
168 | Shop Drawing of Public Address system at 36F | A |  | MEP-495 | 2024-12-19 | 2024-12-26 | A
169 | Shop Drawing of Access Control system at 36F | A |  | MEP-496 | 2024-12-19 | 2024-12-26 | A
II | Plumbing
170 | Shop Drawing of Fire Fighting system layout 36F | A |  | MEP-533 | 2024-12-28 | 2025-01-10 | A
171 | Shop Drawing of Cold & Hot Water Supply system layout 36F | B |  | MEP-544 | 2024-12-31 | 2025-01-10 | C | 2025-01-21 | 2025-01-30 | B
186 | Shop Drawing of Pipe sleeve layout 36F Rev.A | C |  | MEP-555 | 2025-01-22 | 2025-01-30 | C
III | MVAC
187 | Shop Drawing of Air Conditioning system layout 36F | A |  | MEP-507 | 2024-12-23 | 2024-12-26 | A
188 | Shop Drawing of Ventilation system layout 36F | B |  | MEP-508 | 2024-12-23 | 2024-12-26 | B
189 | Shop Drawing of AC Condensate system layout 36F | B |  | MEP-509 | 2024-12-23 | 2024-12-26 | B
N | 36th M Floor
I | Electrical
190 | Shop Drawing of Combined Embedded uPVC conduit for LV & ELV system at 36MF | A |  | MEP-505 | 2024-12-23 | 2024-12-26 | A
191 | Shop Drawing of Lighting system layout 36MF | A |  | MEP-512 | 2024-12-24 | 2025-01-10 | A
192 | Shop Drawing of Socket Outlet layout 36MF | A |  | MEP-513 | 2024-12-24 | 2025-01-10 | A
193 | Shop Drawing of Electrical for MVAC system at 36MF | A |  | MEP-497 | 2024-12-19 | 2024-12-26 | A
194 | Shop Drawing of Fire Alarm system at 36MF | A |  | MEP-498 | 2024-12-19 | 2024-12-26 | A
II | Plumbing
195 | Shop drawing of Waste Water Drainage system layout 36MF | A |  | MEP-489 | 2024-12-19 | 2024-12-19 | A
196 | Shop Drawing of Waste Water Drainage system 37F install under slab 37F layout 36MF | A |  | MEP-529 | 2024-12-28 | 2025-01-10 | A
197 | Shop Drawing of Storm water drainage system layout 36MF | A |  | MEP-530 | 2024-12-28 | 2025-01-10 | A
198 | Shop Drawing of Storm water drainage system layout 37F | A |  | MEP-531 | 2024-12-28 | 2025-01-10 | A
199 | Shop Drawing of Cold & Hot Water Supply system layout 36MF | A |  | MEP-545 | 2024-12-28 | 2025-01-10 | A
200 | Shop Drawing of Fire Fighting system layout 36MF | A |  | MEP-534 | 2024-12-28 | 2025-01-10 | A
201 | Shop Drawing of Cold & Hot Water Supply system layout 36MF | A |  | MEP-545 | 2024-12-31 | 2025-01-10 | A
202 | Shop Drawing of Pipe sleeve layout 36MF Rev.A | C |  | MEP-556 | 2025-01-22 | 2025-01-30 | C
III | MVAC
203 | Shop Drawing of Air Conditioning system layout 36MF | A |  | MEP-507 | 2024-12-23 | 2024-12-26 | A
204 | Shop Drawing of Ventilation system layout 36MF | B |  | MEP-508 | 2024-12-23 | 2024-12-26 | B
205 | Shop Drawing of AC Condensate system layout 36MF | B |  | MEP-509 | 2024-12-23 | 2024-12-26 | B
O | 37th Floor
I | Electrical
206 | Shop Drawing of Combined Embedded uPVC conduit for LV & ELV system at 37F | A |  | MEP-522 | 2024-12-28 | 2025-01-10 | A
207 | Shop Drawing of Internal & External Lighting system layout 37F | A |  | MEP-523 | 2024-12-28 | 2025-01-10 | A
208 | Shop Drawing of Socket Outlet layout 37F | A |  | MEP-524 | 2024-12-28 | 2025-01-10 | A
209 | Shop Drawing of Electrical for MVAC system at 37F | A |  | MEP-525 | 2024-12-28 | 2025-01-10 | A
210 | Shop Drawing of CCTV system at 37F | A |  | MEP-526 | 2024-12-28 | 2025-01-10 | A
211 | Shop Drawing of Access Control system at 37F | A |  | MEP-527 | 2024-12-28 | 2025-01-10 | A
212 | Shop Drawing of Public Address system at 37F | A |  | MEP-528 | 2024-12-28 | 2025-01-10 | A
213 | Shop Drawing of Fire Alarm system at 37F | A |  | MEP-542 | 2024-12-31 | 2025-01-10 | A
II | Plumbing
214 | Shop Drawing of Fire Fighting system layout 37F | A |  | MEP-535 | 2024-12-28 | 2025-01-10 | A
215 | Shop Drawing of Cold & Hot Water Supply system layout 37F | B |  | MEP-546 | 2024-12-31 | 2025-01-10 | B | 2025-01-21 | 2025-01-30 | B
216 | Shop Drawing of Pipe sleeve layout 37F Rev.A | C |  | MEP-557 | 2025-01-22 | 2025-01-30 | C
III | MVAC
217 | Shop Drawing of the Air Conditioning System Layout 37F | A |  | MEP-519 | 2024-12-28 | 2025-01-10 | A
218 | Shop Drawing of the Ventilation System Layout 37F | A |  | MEP-520 | 2024-12-28 | 2025-01-10 | A
219 | Shop Drawing of the AC Condensate System Layout 37F | A |  | MEP-521 | 2024-12-28 | 2025-01-10 | A
P | 37th M Floor
I | Electrical
220 | Shop Drawing of Combined Embedded uPVC conduit for LV & ELV system at 37MF | A |  | MEP-536 | 2024-12-28 | 2025-01-10 | A
221 | Shop Drawing of Internal Lighting system layout 37MF | A |  | MEP-537 | 2024-12-28 | 2025-01-10 | A
222 | Shop Drawing of Socket Outlet layout 37MF | A |  | MEP-539 | 2024-12-28 | 2025-01-10 | A
223 | Shop Drawing of CCTV system at 37MF | A |  | MEP-540 | 2024-12-28 | 2025-01-10 | A
224 | Shop Drawing of Fire Alarm system at 37MF | A |  | MEP-541 | 2024-12-28 | 2025-01-10 | A
225 | Shop Drawing of Access Control system at 37MF | A |  | MEP-543 | 2024-12-31 | 2025-01-10 | A
II | Plumbing
226 | Shop Drawing of Cold & Hot Water Supply system layout 37MF | C |  | MEP-547 | 2024-12-31 | 2025-01-10 | C | 2025-01-21 | 2025-01-30 | C
III | MVAC
Q | Roof Floor
227 | Shop Drawing of External Lighting system layout RF | A |  | MEP-538 | 2024-12-28 | 2025-01-10 | A

## MAR MEP
PROJECT | : THE VIEW II
SUBJECT | : MATERIAL MEP MONITORING | [16 empty] | 63.27% | A | : Approval
MAIN-CON | : SOMA CONSTRUTION & DEVELOPMENT CO., LTD | [16 empty] | 10.2% | B | : Approved with comment
CLIENT | : HOHSIN DEVELOPMENT CO., LTD | [16 empty] | 14.29% | C | : Return/Reject
LOCATION | : #13, ST. 588 CORNER ST.307, PHUM 11, BOEUNG KAK 2, KHAN TOUL KOK, PHNOM PENH | [16 empty] | 6.122% | U/R | : Under Review
PROGRESS | :02/28/2025 | [16 empty] | 49 | Infor. | : For information
No. | MATERIAL DESCRIPTION | BRAND/COMPANY | LASTEST APPROVAL STATUS | SUBMISSION DATE | Number table | DT.No. | Rev.A |  |  | Rev.B |  |  | Rev.C |  |  | Rev.D |  |  | COMMENT | REMARK
[7 empty] | SUBMITTED DATE | RETURNED DATE | STATUS | SUBMITTED DATE | RETURNED DATE | STATUS | SUBMITTED DATE | RETURNED DATE | STATUS | SUBMITTED DATE | RETURNED DATE | STATUS
A | MAR OF ELECTRICAL SYSTEM
A.1 | MAR OF LV SYSTEM
1 | Material uPVC conduit and fitting for electrical system | MP | A | 2023-07-27 | 5207-M(2) | MEP-031 | 2023-07-27 | 2023-07-27 | A
2 | Material Lightning | Kumwell | A | 2020-02-05 | 5207-M(1) | MEP-001 | 2020-01-20 | 2020-02-05 | A
3 | Material Cu/PVC cable for earthing | Kumwell | A | 2020-02-05 | 5207-M(1) | MEP-002 | 2020-01-20 | 2020-02-05 | A
4 | Material PVC conduit for electrical wiring | MP | A | 2020-04-04 | 5207-M(1) | MEP-006 | 2020-02-12 | 2020-02-17 | C | 2020-04-04 | 2020-04-05 | A
5 | Material: Wiring device | CHINT | C | 2023-11-23 | 5207-M(2) | MEP-140 | 2023-11-21 | 2023-11-23 | C
6 | Material: Wiring device | Legrand | A |  |  | MEP-139 | 2023-11-21 |  | A
7 | Material Low Voltage cable | Tai Sin | A | 2023-09-06 | 5207-M(2) | MEP-061 | 2023-09-05 | 2023-09-06 | A
8 | Material Low Voltage cable | Keystone | A | 2023-09-06 | 5207-M(2) | MEP-060 | 2023-09-05 | 2023-09-06 | A
9 | Letter Material approval LV cable |  | Infor. |  | 5207-M(2) | MEP-445
10 | Material:Sub-distribution board | Scheider |  |  |  | MEP-179 | 2023-12-04 |  | U/R
11 | Material: Perforated Cable tray Thk 1.2mm | KHMER ENGINEER | A | 2024-02-08 |  | MEP-205 | 2024-01-04 | 2024-02-08 | A
12 | Material: Lighting Fixture |  | B | 2024-04-25 |  | MEP-279 | 2024-04-08 | 2024-04-25 | B
13 | Material: Sub distribution board (Inside Unit) | Mekong automation | A | 2024-04-25 |  | MEP-280 | 2024-04-18 | 2024-04-25 | A
A.2 | MAR OF ELV SYSTEM
I | CCTV SYSTEM
1 | Network Cable (Cat6 23 AWG) | Nexans | A | 2023-12-25 |  | MEP-196 | 2023-12-25 | 2024-01-02 | A
2 | Material Approval of CCTV system | OBT | U/R | 2024-09-17 |  | MEP-272 | 2024-03-04 | 2024-03-14 | C | 2024-09-17 |  | U/R
II | FIRE ALARM SYSTEM
1 | Material of Fire resistant cable for fire alarm cable | Norden | A | 2023-11-15 | 5207-M(2) | MEP-134 | 2023-11-15 | 2023-11-29 | A
2 | Material of Fire Alarm system | Nohmi | A | 2024-01-29 |  | MEP-246 | 2024-01-29 | 2024-02-01 | A
III | PUBLIC ADDRESS SYSTEM
1 | Public Address Cable | Nexans | A | 2023-12-20 |  | MEP-193 | 2023-12-20 | 2024-01-02 | A
2 | Public Address system | OBT | A | 2024-09-27 |  | MEP-274 | 2024-03-04 | 2024-03-14 | C | 2024-09-27 | 2025-01-13 | C | 2025-01-17 | 2025-01-27 | A
IV | ACCESS CONTROL SYSTEM
1 | Material of cat 6 cable 23AWG | Nexans | A | 2023-12-25 |  | MEP-196 | 2023-12-25 | 2024-01-02 | A
2 | Material of Twisted pairs shield 2x18 AWG | Planec | A | 2024-01-19 |  | MEP-241 | 2024-01-19 | 2024-03-14 | A
3 | Access Control system | OBT,AWS | A | 2024-06-11 |  | MEP-273 | 2024-06-11 | 2024-09-05 | C | 2024-07-25 | 2024-08-08 | C | 2024-08-20 | 2024-09-02 | B | 2024-09-05 | 2024-09-05 | A |  |  | Change supplier OBT to AWS by first submit Rev.A (Sub: 4-March Return: 14- March)(Supplier OBT)
V | DATA SYSTEM
1 | Material of cat 6 cable 23AWG | Nexans | A | 2023-12-20 |  | MEP-193 | 2023-12-20 | 2024-01-02 | A
2 | Material Data and WiFi system | KH TECH Co., Ltd | U/R | 2024-09-06 |  | MEP-371 | 2024-09-06 |  | U/R
3 | Material Floor standing server Rack and PDU | OBT | A | 2024-10-10 |  | MEP-421 | 2024-10-10 | 2024-10-31 | C | 2024-11-12 | 2024-11-21 | A
4 | Material Fiber optic Cable | Nexans brand | A | 2024-12-19 |  | MEP-501 | 2024-12-19 | 2024-12-26 | A
VI | MATV SYSTEM
1 | Material of Coaxial cable (RG-6 & RG-11) | Interlink | A | 2024-01-19 |  | MEP-239 | 2024-01-19 | 2024-03-14 | A
VII | TELEPHONE SYSTEM
1 | Material of Cat 3 UTP 2 pair | Alantek | C | 2024-01-19 |  | MEP-240 | 2024-01-19 | 2024-02-22 | C
B | MAR OF PLUMBING SYSTEM
1 | Material PVC pipe product | SCG | A | 2020-04-04 | 5207-M(1) | MEP-010 | 2020-04-04 | 2020-04-05 | A
2 | Material Selection & specifition |  | C | 2020-09-20 | 5207-M(1) | MEP-009 | 2020-09-20 | 2020-09-26 | C
2 | Material PPR Pipe and fitting | Polygon | A | 2023-06-21 | 5207-M(1) | MEP-019 | 2020-10-19 | 2020-11-12 | C | 2023-06-21 | 2023-06-22 | A
3 | Material of superswell 47B |  | A | 2023-08-11 | 5207-M(1) | MEP-040 | 2023-08-11 | 2023-08-12 | A
4 | Material SCG pipe and fitting | SCG | B | 2023-07-12 | 5207-M(2) | MEP-029 |  |  |  | 2023-07-12 | 2023-07-13 | B
5 | Material Transfer Pump | Ebara | C | 2023-07-31 | 5207-M(2) | MEP-033 | 2023-07-31 | 2023-07-31 | C
6 | Material Supmersible Pump | Ebara | B | 2023-07-31 | 5207-M(2) | MEP-034 | 2023-07-31 | 2023-07-31 | B
7 | Material Of Septic Tank |  | B | 2023-11-24 | 5207-M(2) | MEP-063 | 2023-09-08 | 2023-09-12 | C | 2023-11-24 | 2023-12-23 | B
8 | Material: HDPE pipe and fitting | TAP | A | 2023-08-28 | 5207-M(2) | MEP-052 | 2023-08-28 | 2023-08-30 | A
9 | Material: Electric water storage heater | Rinnai | A | 2024-01-03 |  | MEP-203 | 2024-01-03 | 2024-01-08 | A
10 | Septic Tank | Biotech | B | 2023-11-24 |  | MEP-203 | 2023-11-24 | 2023-12-12 | B
11 | Fire Sprinkler Head | TEM | U/R | 2024-07-25 |  | MEP-322 | 2024-06-12 | 2024-06-27 | C | 2024-07-11 | 2024-07-18 | C | 2024-07-25 |  | U/R
12 | Fire Extinguisher (ABC & CO2) | TEM | A | 2024-10-10 |  | MEP-422 | 2024-10-10 | 2024-10-31 | C | 2024-11-12 | 2024-11-21 | A
13 | Cold Water Storage Tank | MAGTECH GENERAL | A |  |  | MEP-482 | 2024-12-07 | 2024-12-19 | C | 2024-12-23 | 2024-12-26 | A
14 | Material Accessories valve | TEM | C |  |  | MEP-551 | 2025-01-21 | 2025-01-30 | C
C | MAR OF MVAC SYSTEM
1 | Material of Copper pipe | Hailiang | A | 2024-02-27 |  | MEP-213 | 2024-01-06 | 2024-01-11 | C | 2024-02-27 | 2024-03-05 | A
2 | Material of Insulation Tube Thk 13mm | Superlon | A | 2024-02-27 |  | MEP-214 | 2024-01-06 | 2024-01-11 | C | 2024-02-27 | 2024-03-05 | A
3 | Material submittal of Air Conditioner | Panasonic | C | 2024-08-01 |  | MEP-296 | 2024-05-27 | 2024-07-10 | C | 2024-08-01 | 2024-08-08 | C
4 | Ventialtion system | Kruger | C | 2024-06-03 |  | MEP-317 | 2024-06-03 | 2024-06-27 | C
5 | Fire Hose Reel and Fire Hose Reel Cabinet | TEM | A |  |  | MEP-432 | 2024-10-21 | 2024-10-31 | B | 2024-11-12 | 2024-11-21 | A
D | MEP SAMPLE BOARD
1 | Sample board of uPVC conduit and fitting |  | Infor. |  | 5207-M(2) | MEP-047

## NCR & RFI
PROJECT | : THE VIEW II
SUBJECT | : RFI, NCR MEP MONITORING | [10 empty] | 0% | A | : Approval
MAIN-CON | : SOMA CONSTRUTION & DEVELOPMENT CO., LTD | [10 empty] | 50% | B | : Approved with comment
CLIENT | : HOHSIN DEVELOPMENT CO., LTD | [10 empty] | 0% | C | : Return/Reject
LOCATION | : #13, ST. 588 CORNER ST.307, PHUM 11, BOEUNG KAK 2, KHAN TOUL KOK, PHNOM PENH | [10 empty] | 0% | U/R | : Under Review
PROGRESS | 2025-02-20 | [10 empty] | 2 | Infor. | : For information
No. | DESCRIPTION | LASTEST APPROVAL STATUS | DT.No. | Rev.A |  |  | Rev.C | [5 empty] | COMMENT | REMARK
|  |  |  | FROM HS TO SMCD |  |  | FROM HS TO SMCD |  |  | SMCD TO HS
|  |  |  | SUBMITTED DATE | RETURNED DATE | STATUS | SUBMITTED DATE | RETURNED DATE | STATUS | SUBMITTED DATE | RETURNED DATE | STATUS
A | REQUEST FOR INFORMATION (RFI)
1 | Request for using temporary tank ( Fire Fighting) Rev.C | B | MEP-176 | [6 empty] | 2023-12-02 | 2023-12-07 | B
2 | Request for Changing Part Number of Fire-Resistant Cable |  | MEP-287 | 2024-03-21
B | NON-CONFORMANCE REPORT (NCR)

## REQUEST FOR INSPECTION (RI)
PROJECT | : THE VIEW II
SUBJECT | : REQUEST FOR INSPECTION OF MEP MONITORING | [7 empty] | #DIV/0! | A | : Approval
MAIN-CON | : SOMA CONSTRUTION & DEVELOPMENT CO., LTD | [7 empty] | #DIV/0! | B | : Approved with comment
CLIENT | : HOHSIN DEVELOPMENT CO., LTD | [7 empty] | #DIV/0! | C | : Return/Reject
LOCATION | : #13, ST. 588 CORNER ST.307, PHUM 11, BOEUNG KAK 2, KHAN TOUL KOK, PHNOM PENH | [7 empty] | #DIV/0! | U/R | : Under Review
PROGRESS | 2025-02-20 | [7 empty] | 0 | Infor. | : For information
No. | DESCRIPTION | LASTEST APPROVAL STATUS | DT.No. | Rev.A |  |  | Rev.B |  |  | COMMENT | REMARK
|  |  |  | SUBMITTED DATE | RETURNED DATE | STATUS | SUBMITTED DATE | RETURNED DATE | STATUS
A | REQUEST FOR INSPECTION (RI)

## SMCD INTERNAL WORK
PROJECT | : THE VIEW II
SUBJECT | : SMCD INTERNAL WORK (MEP-AA) | [12 empty] | #DIV/0! | A | : Approval
MAIN-CON | : SOMA CONSTRUTION & DEVELOPMENT CO., LTD | [12 empty] | #DIV/0! | B | : Approved with comment
CLIENT | : HOHSIN DEVELOPMENT CO., LTD | [12 empty] | #DIV/0! | C | : Return/Reject
LOCATION | :#13, ST. 588 CORNER ST.307, PHUM 11, BOEUNG KAK 2, KHAN TOUL KOK, PHNOM PENH | [12 empty] | #DIV/0! | U/R | : Under Review
PROGRESS | 2025-02-20 | [12 empty] | 0 | Infor. | : For information
No. | DESCRIPTION | LASTEST APPROVAL STATUS | Rev.A | [5 empty] | Rev.B | [5 empty] | COMMENT | REMARK
|  |  | FROM MEP TO AA |  |  | FROM AA TO MEP |  |  | FROM MEP TO AA |  |  | FROM AA TO MEP
|  |  | SUBMITTED DATE | RETURNED DATE | STATUS | SUBMITTED DATE | RETURNED DATE | STATUS | SUBMITTED DATE | RETURNED DATE | STATUS | SUBMITTED DATE | RETURNED DATE | STATUS
A | SMCD INTERNAL WORK (MEP-AA)